## Product Backlog
UserStoryID | User Story | Story Points | Sprint | Status | Expected Date Completion | Actual Date Completion | Total Points | Avg Points to Complete per Week
1 | As an admin/owner, I want to have a clear design proposal describing the final artiafact | 10 | 1 | Complete | 2020-01-26 | 2020-01-26 | 772 | 64.3333
2 | As a user, I want a stylish, clean user interface | 22 | 2 | Complete | 2020-01-31 | 2020-01-28
3 | As a developer, I want the product to be coded to a high standard using good coding practices | 20 | 2 | Complete | 2020-02-01 | 2020-01-28
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 120 | 1,2 | Complete | 2020-02-12 | 2020-01-31
5 | As a user, I want to be able to see the current temperatures from each different sensor on a graph | 30 | 2 | Complete | 2020-02-16 | 2020-01-02
6 | As a user, I want to be able to see previous temperatures as text outputs | 20 | 3 | Complete | 2020-02-23 | 2020-02-03
7 | As a user, I want to be able to see previous temperatures on a graph | 10 | 3 | Complete | 2020-02-23 | 2020-02-03
8 | As a user, I want to be able to start and stop the logging of temperature data | 15 | 3 | Complete | 2020-02-26 | 2020-02-06
9 | As a user, I want to be able to configure how many sensors are in use | 50 | 4 | Complete | 30/02/2020 | 2020-02-13
10 | As a user, I want to be able to filter the date and time ranges to search for previous temperatures between | 15 | 4 | Complete | 2020-03-04 | 2020-02-16
11 | As a user, I want a connection status bar indicating if the current device is connected, connecting or failed to connect | 35 | 5 | Complete | 2020-03-08 | 2020-02-19
12 | As a user, I want to see the GPS data for each temperature sensor | 40 | 5 | Complete | 2020-03-12 | 2020-02-23
13 | As a user, I want outliers being read into the C# application are automatically removed | 40 | 6 | Complete | 2020-03-15 | 2020-02-25
14 | As a user, I want the data to be stored on the sensor when the connection between the sensor and the computer fails for quality assurances | 40 | 6 | Complete | 2020-03-17 | 2020-02-27
15 | As a user, I want to see data statistics to help understand the recorded data | 40 | 6 | Complete | 2020-03-22 | 2020-03-01
16 | As an admin, I want to record the exact date and time the data was recorded (DateTimeModule on sensor) | 20 | 7 | Complete | 2020-03-25 | 2020-03-03
17 | As a admin/developer, I want the data to be stored in SQL databses locally on the device and in the cloud | 15 | 3,8 | Complete | 2020-03-25
18 | As an admin, I wan to see clear evidence of human validation checking and automated validation checking (Unit tests) | 30 | 7 |  | 2020-03-29
19 | As a user/data scientist, I want to be able to see a breakdown of the data. (I.e. data models, machine learning models, stats etc) | 70 | 7,8,9
20 | As a user, I want to see the location on a map where the temperature was recorded | 40 | 7,8,9
21 | As a admin/developer, I want clear documentation on how to configure the arduino boards | 30 | 9,10,11
22 | As an admin/developer, I want clear documentation on how to application works (WPF App) | 30 | 9,10,11
23 | As an admin/developer, I want diagrams and explination of how the system is structured | 30 | 9,10,11

## Sprint One
Sprint One
Sprint Dates: | 20/01/2020 - 26/01/2020
Sprint Goal
By the end of this sprit, the user interface designs should be completed along with the design proposal. Also I wish to have the Arduino setup with the thermocouple attached
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 20/01/2020 | 21/01/2021 | 22/01/2022 | 23/01/2023 | 24/01/2024 | 25/01/2025 | 26/01/2026 | Done (Y) | Mon | 6 | 64 | 60
1 | As an admin/owner, I want to have a clear design proposal describing the final artiafact | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 2 |  | Tues | 6 | 58 | 50
| Find useful references online | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y | Wed | 29 | 29 | 40
| Explain the companies criteria | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Y | Thur | 6 | 23 | 30
| Develop project plan with key dates | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | Y | Fri | 6 | 17 | 20
| Write rest of proposal | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 17 | 10
[11 empty] | Sun | 12 | 0 | 0
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 60 | 5 | 5 | 25 | 5 | 5 | 0 | 10
| Order and obtain all hardware Arduino parts | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Research and understand Arduino and all the parts | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Points Each Day | 10
| Complete a beginnners/basic Arduino tutorial | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y
| Solder the Thermocouple breakout board to the Thermocouple connector | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y
| Solder the connnector pins to the Thermocouple breakout board | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y
| Connect the Thermocouple breakout board to the Arduino using jumper cables | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Develop the code to read the current temperature and output to the serial monitor in the Arduino IDE | 20 | 0 | 0 | 0 | 5 | 5 | 0 | 10 | Y
| Story Points Remaining |  | 6 | 6 | 29 | 6 | 6 | 0 | 12

## Sprint Two
Sprint One
Sprint Dates: | 27/01/2020 - 02/02/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I wish to have the WPF application setup with a style user interface applied to the MainWindow. I wish to setup the architecture of the application. | [5 empty] | During this sprint I have ove achieved my aim. I have successfully read data from the bluetooth device into the WPF application which I thought would take longer
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-03-02 | Done (Y) | Mon | 28 | 94 | 104.5714
2 | As a user, I want a stylish, clean user interface | 22 | 14 | 8 | 0 | 0 | 0 | 0 | 0 |  | Tues | 14 | 80 | 87.1429
| Create WPF Project | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 14 | 66 | 69.7143
| Create style folder | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 12 | 54 | 52.2857
| Create resource dictionary for each component | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Y | Fri | 34 | 20 | 34.8571
| Create base style for each component | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 20 | 17.4286
| Create a merged resource dictionary | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Sun | 20 | 0 | 0
| Style the MainWindow and setup navigation | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | Y
3 | As a developer, I want the product to be coded to a high standard using good coding practices | 20 | 14 | 6 | 0 | 0 | 0 | 0 | 0 |  | Points Each Day | 17.4286
| Create separate projects for ViewModels and Models | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Implement the MVVM pattern for the WPF project | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Create a repository layer for data submission to the database | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Link the projects togheter | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Setup the inbuilt dependency injection feature with .Net Core apps | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Y
| Create data templerate for views with corresponding DataContext (ViewModels) | 4 | 2 | 2 |  | 0 | 0 | 0 | 0 | Y
| Add RelayCommand class for Button Execution | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Add ViewModelBase that each ViewModel should inherit from | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| The navigation buttons add command to chage view in ContentControl | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Y
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 60 | 0 | 0 | 14 | 12 | 34 | 0 | 0
| Connect the bluetooth module to the Arduino board | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Connect the Arduino to the nearby windows device | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Install 32Feet library to WPF Project | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y
| Create new BluetoothService project in solution | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y
| Develop class, BluetoothFinder.cs, to search for nearby bluetooth device matching a specified criteria | 15 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | Y
| Develop class, RecieverBluetoothService.cs, to read the current bluetooth data using a NetworkStream. | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | Y
| Retrieve the latest value from the bluetooth network stream | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | Y
| Add latest value to an Observable collection of strings to output to the user on-screen | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | Y
5 | As a user, I want to be able to see the current temperatures from each different sensor on a graph | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
| Install OxyPlot | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Y
| Read the OxyPlot documentation and find tutorial | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Y
| Create new ObservableCollection of type DataPoint | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Y
| When a new latest reading has been retrieved add the temperature and time to the DataPoints Observable collection | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Y
| Bind the observable collection to the graph on the view | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Y
| Story Points Remaining | 122 | 28 | 14 | 14 | 12 | 34 | 0 | 20

## Sprint Three
Sprint One
Sprint Dates: | 03/02/2020 - 09/02/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I want to be able to store the temperature data locally in an SQL database and display the history temperature data to the user
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | Done (Y) | Mon | 20 | 45 | 55.7143
17 | As a admin/developer, I want the data to be stored in SQL databses locally on the device and in the cloud | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | Tues | 10 | 35 | 46.4286
| Design database structure | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 10 | 25 | 37.1429
| Create ShellTemperature class with all properties that need to be stored in the database | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 2 | 23 | 27.8571
| Create ShellDb class that represents the database | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Fri | 13 | 10 | 18.5714
| Using EntityFramework, add a migration and update the database | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 10 | 9.2857
| Add code on startup to add migrations to database if needed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Sun | 0 | 0 | 0
| Adjust code, after the temperature is retrieved store the data in the local SQL database | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y
6 | As a user, I want to be able to see previous temperatures as text outputs | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 |  | Points Each Day | 9.2857
| Create a new UserControl to display history temperatures | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | Y
| Create new ViewModel for history temperatures | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Y
| Retrieve all previous temperatures from the SQL database and display in ObservableCollection | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | Y
7 | As a user, I want to be able to see previous temperatures on a graph | 20 | 0 | 0 | 10 | 0 | 0 | 0 | 0
| Create new ObservableCollection to hold data points for graphs | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Add all of the retrieved data from the SQL database to the new ObservableCollection | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
8 | As a user, I want to be able to start and stop the logging of temperature data | 15 | 0 | 0 | 0 | 2 | 13 | 0 | 0
| Create a start and stop button on the LiveShell UserControl | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Y
| Create two commands to start and stop the timer thread retrieving the latest temperature | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | Y
| Stop the thread when the stop button is pressed | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | Y
| Start the thread when the start button is pressed | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Story Points Remaining | 65 | 20 | 10 | 10 | 2 | 13 | 0 | 0

## Sprint Four
Sprint One
Sprint Dates: | 10/02/2020 - 16/02/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I want to be able to read live data into the application from multiple bluetooth devices. I also want the user to be able filter the history data by date.
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | Done (Y) | Mon | 10 | 55 | 55.7143
9 | As a user, I want to be able to configure how many sensors are in use | 50 | 10 | 15 | 25 | 0 | 0 | 0 | 0 |  | Tues | 15 | 40 | 46.4286
| Create a second temperature sensor. Solder the parts togheter and upload the existing code to the Arduino board. The same procedure as week one | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 25 | 15 | 37.1429
| Add section to configuration file that specifies the name of the bluetooth device to search for | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 4 | 11 | 27.8571
| Add a section to the configuration file that matches the BluetoothId to a Recognisable name | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y | Fri | 4 | 7 | 18.5714
| Adjust the BluetoothFinder class to search for multiple bluetooth devices based upon the bluetooth device information in the configuration file | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 7 | 9.2857
| Run each separate bluetooth device found on a separate timer thread | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y | Sun | 7 | 0 | 0
| Add dropdown menu to the LiveShellUserControl to switch between the active bluetooth device data being displayed | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y
10 | As a user, I want to be able to filter the date and time ranges to search for previous temperatures between | 15 | 0 | 0 | 0 | 4 | 4 | 0 | 7 |  | Points Each Day | 9.2857
| Find a library to use to create/display a good quality datetime picker in WPF as the inbuilt is poor | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Y
| Add the DateTime picker to the ShellHistoryUserControl | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Y
| Apply styling to the DateTime pickers | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | Y
| Bind the Start and End datetime properties to the DateTime pickers | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | Y
| Each time the DateTime picker is changed on the view, update the Data values between those dates | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Y
| Add validation to prevent start date being after end date and vice-versa. | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Y
| Story Points Remaining | 65 | 10 | 15 | 25 | 4 | 4 | 0 | 7

## Sprint Five
Sprint One
Sprint Dates: | 17/02/2020 - 23/02/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I want to be able to record the GPS location of the sensor device. I also want to be able to display a connection status bar at the top of the view to indicate to the user whether the current device is still connected, failed to connect or encountered an error.
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | Done (Y) | Mon | 5 | 70 | 64.2857
11 | As a user, I want a connection status bar indicating if the current device is connected, connecting or failed to connect | 35 | 5 | 10 | 20 | 0 | 0 | 0 | 0 |  | Tues | 10 | 60 | 53.5714
| Add a UserControl to act as the conenction status bar | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 21 | 39 | 42.8571
| Create a ViewModel for the connection status and bind to the userconntrol | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 9 | 30 | 32.1429
| Implement the observer pattern to update the connection status from another viewmodel | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | Y | Fri | 20 | 10 | 21.4286
| Add the feature, when a connection is successful and data is being read the bar is green with a positive message | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 10 | 10.7143
| Add the feature, when the connection has failed, a red bar appears with a negative message | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y | Sun | 10 | 0 | 0
| Add the feature, when the connection is connecting the bar is orange with a neutral message | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
12 | As a user, I want to see the GPS data for each temperature sensor | 40 | 0 | 0 | 1 | 9 | 20 | 0 | 10 |  | Points Each Day | 10.7143
| Obtain the GPS Sheild | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Y
| Attach the GPS Shield to the Arduino board | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Y
| Reconnect the Bluetooth and Thermocouple modules to the GPS Shield | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Y
| Develop C++ code to read the current latitude and longitude of the sensor device | 10 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | Y
| Add the latitude and longitude to the output stream if it has successfully been retrieved. | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| In the C# WPF application, read in the latitude and longitude if they are there | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | Y
| Store the latitude and longitude in the SQL database alongside the temperature reading | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | Y
| Display the current latitude and longitude of the device to the user | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Y
| Add ToolTip to temperatures to show information about the GPS location | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Y
| Story Points Remaining | 75 | 5 | 10 | 21 | 9 | 20 | 0 | 10

## Sprint Six
Sprint One
Sprint Dates: | 24/02/2020 - 01/03/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I want to be able to automatically remove outliers, store data on a SD card if the connection between the sensor and the PC fails, and show the user data statistics of the recorded data.
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | Done (Y) | Mon | 20 | 100 | 102.8571
13 | As a user, I want outliers being read into the C# application are automatically removed | 40 | 20 | 20 | 0 | 0 | 0 | 0 | 0 |  | Tues | 27 | 73 | 85.7143
| Calculate the interquantile range of a data set | 30 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 31 | 42 | 68.5714
| Use a multiplier to find the lower bound and upper bound for the interquantile range | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 8 | 34 | 51.4286
| Determine if the latest value read in is an outlier based of the lower and upper bound of the interquantile range | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y | Fri | 25 | 9 | 34.2857
[11 empty] | Sat | 0 | 9 | 17.1429
14 | As a user, I want the data to be stored on the sensor when the connection between the sensor and the computer fails for quality assurances | 40 | 0 | 7 | 31 | 7 | 0 | 0 | 0 |  | Sun | 14 | 0 | 0
| Connect the bluetooths module state pin to the Arduino GPS Sheidl | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Y
| Read the state pins value. 1 or greater indicates a connection, 0 indicates no bluetooth connection | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y
| Insert the SD card and add the code needed to read and write to the file | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | Y | Points Each Day | 17.1429
| If the bluetooth state is 0 write the current temperature and GPS location to the SD card | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | Y
| If the bluetooth state is 1 then read the data from the SD card if it is there, once complete then delete the text file from the SD card | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | Y
| Adjust the C# WPF code to handle reading data from the SD card. Look for the tag specifying -sdCardData | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | Y
15 | As a user, I want to see data statistics to help understand the recorded data | 40 | 0 | 0 | 0 | 1 | 25 | 0 | 14
| Setup the classes needed to calculate the data statistics | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Y
| Develop a mean average method | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Develop a mode method | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Develop a median method | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Develop a range method | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Develop a mean deviation method | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | Y
| Develop a standard deviation method | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Y
| Fine tune the interquantile range method | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| Create a property in the Report ViewModel for each data statistic above | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Retrieve the temperature values between a date range and calculate all data statistics and output to the user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Story Points Remaining | 120 | 20 | 27 | 31 | 8 | 25 | 0 | 14