## Product Backlog
UserStoryID | User Story | Story Points | Sprint | Status | Expected Date Completion | Actual Date Completion
1 | As an admin/owner, I want to have a clear design proposal describing the final artiafact | 10 | 1 | Complete | 2020-01-26 | 2020-01-26
2 | As a user, I want a stylish, clean user interface | 22 | 2 | Complete | 2020-01-31 | 2020-01-28
3 | As a developer, I want the product to be coded to a high standard using good coding practices | 20 | 2 | Complete | 2020-02-01 | 2020-01-28
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 120 | 1,2 | Complete | 2020-02-12 | 2020-01-31
5 | As a user, I want to be able to see the current temperatures from each different sensor on a graph | 30 | 2 | Complete | 2020-02-16 | 2020-01-02
6 | As a user, I want to be able to see previous temperatures as text outputs | 20 | 3 | Complete | 2020-02-23 | 2020-02-03
7 | As a user, I want to be able to see previous temperatures on a graph | 20 | 3 | Complete | 2020-02-23 | 2020-02-03
8 | As a user, I want to be able to start and stop the logging of temperature data | 15 | 3 | Complete | 2020-02-26 | 2020-02-06
9 | As a user, I want to be able to configure how many sensors are in use | 50 | 4 | Complete | 30/02/2020 | 2020-02-13
10 | As a user, I want to be able to filter the date and time ranges to search for previous temperatures between | 15 | 4 | Complete | 2020-03-04 | 2020-02-16
11 | As a user, I want a connection status bar indicating if the current device is connected, connecting or failed to connect | 40 | 5 | Complete | 2020-03-08 | 2020-02-19
12 | As a user, I want to see the GPS data for each temperature sensor | 30 | 5 | Complete | 2020-03-12 | 2020-02-21
13 | As a user, I want outliers being read into the C# application are automatically removed | 60 | 6 | Complete | 2020-03-15 | 2020-02-25
14 | As a user, I want the data to be stored on the sensor when the connection between the sensor and the computer fails for quality assurances | 40 | 6 | Complete | 2020-03-17 | 2020-02-27
15 | As a user, I want to see data statistics to help understand the recorded data | 40 | 6 | Complete | 2020-03-22 | 2020-03-01
16 | As an admin, I want to record the exact date and time the data was recorded (DateTimeModule on sensor) | 20 | 7 | Complete | 2020-03-25 | 2020-03-03
| As a admin/developer, I want the data to be stored in SQL databses locally on the device and in the cloud | 30 | 2,8 | Complete | 2020-03-25
17 | As an admin, I wan to see clear evidence of human validation checking and automated validation checking (Unit tests) | 30 | 7 |  | 2020-03-29
18 | As a user/data scientist, I want to be able to see a breakdown of the data. (I.e. data models, machine learning models, stats etc) | 70 | 7,8,9
19 | As a user, I want to see the location on a map where the temperature was recorded | 40 | 7,8,9
20 | As a admin/developer, I want clear documentation on how to configure the arduino boards | 30 | 9,10,11
21 | As an admin/developer, I want clear documentation on how to application works (WPF App) | 30 | 9,10,11
22 | As an admin/developer, I want diagrams and explination of how the system is structured | 30 | 9,10,11

## Sprint One
Sprint One
Sprint Dates: | 20/01/2020 - 26/01/2020
Sprint Goal
By the end of this sprit, the user interface designs should be completed along with the design proposal. Also I wish to have the Arduino setup with the thermocouple attached
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 20/01/2020 | 21/01/2021 | 22/01/2022 | 23/01/2023 | 24/01/2024 | 25/01/2025 | 26/01/2026 | Done (Y) | Mon | 6 | 64 | 60
1 | As an admin/owner, I want to have a clear design proposal describing the final artiafact | 10 | 1 | 1 | 4 | 1 | 1 | 0 | 2 |  | Tues | 6 | 58 | 50
| Find useful references online | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y | Wed | 29 | 29 | 40
| Explain the companies criteria | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Y | Thur | 6 | 23 | 30
| Develop project plan with key dates | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | Y | Fri | 6 | 17 | 20
| Write rest of proposal | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 17 | 10
[11 empty] | Sun | 12 | 0 | 0
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 60 | 5 | 5 | 25 | 5 | 5 | 0 | 10
| Order and obtain all hardware Arduino parts | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Research and understand Arduino and all the parts | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Points Each Day | 10
| Complete a beginnners/basic Arduino tutorial | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | Y
| Solder the Thermocouple breakout board to the Thermocouple connector | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y
| Solder the connnector pins to the Thermocouple breakout board | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | Y
| Connect the Thermocouple breakout board to the Arduino using jumper cables | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Develop the code to read the current temperature and output to the serial monitor in the Arduino IDE | 20 | 0 | 0 | 0 | 5 | 5 | 0 | 10 | Y
| Story Points Remaining |  | 6 | 6 | 29 | 6 | 6 | 0 | 12

## Sprint Two
Sprint One
Sprint Dates: | 27/01/2020 - 02/02/2020
Sprint Goal | [5 empty] | Sprint Comments
By the end of the sprint I wish to have the WPF application setup with a style user interface applied to the MainWindow. I wish to setup the architecture of the application. | [5 empty] | During this sprint I have ove achieved my aim. I have successfully read data from the bluetooth device into the WPF application which I thought would take longer
Feature Burndown - Based on stroy points completed
|  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun |  | Days of week | Points per day | Points Remaining | Average points remaining
UserStoryID | Task | Story Points | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-03-02 | Done (Y) | Mon | 28 | 94 | 104.5714
2 | As a user, I want a stylish, clean user interface | 22 | 14 | 8 | 0 | 0 | 0 | 0 | 0 |  | Tues | 14 | 80 | 87.1429
| Create WPF Project | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Wed | 14 | 66 | 69.7143
| Create style folder | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Thur | 12 | 54 | 52.2857
| Create resource dictionary for each component | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Y | Fri | 34 | 20 | 34.8571
| Create base style for each component | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Y | Sat | 0 | 20 | 17.4286
| Create a merged resource dictionary | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Sun | 20 | 0 | 0
| Style the MainWindow and setup navigation | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | Y
3 | As a developer, I want the product to be coded to a high standard using good coding practices | 20 | 14 | 6 | 0 | 0 | 0 | 0 | 0 |  | Points Each Day | 17.4286
| Create separate projects for ViewModels and Models | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Implement the MVVM pattern for the WPF project | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Create a repository layer for data submission to the database | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Link the projects togheter | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Setup the inbuilt dependency injection feature with .Net Core apps | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Y
| Create data templerate for views with corresponding DataContext (ViewModels) | 4 | 2 | 2 |  | 0 | 0 | 0 | 0 | Y
| Add RelayCommand class for Button Execution | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| Add ViewModelBase that each ViewModel should inherit from | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Y
| The navigation buttons add command to chage view in ContentControl | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Y
4 | As a user, I want to be able to see the current temperatures from each different sensor as a text output | 60 | 0 | 0 | 14 | 12 | 34 | 0 | 0
| Connect the bluetooth module to the Arduino board | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Connect the Arduino to the nearby windows device | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | Y
| Install 32Feet library to WPF Project | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y
| Create new BluetoothService project in solution | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Y
| Develop class, BluetoothFinder.cs, to search for nearby bluetooth device matching a specified criteria | 15 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | Y
| Develop class, RecieverBluetoothService.cs, to read the current bluetooth data using a NetworkStream. | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | Y
| Retrieve the latest value from the bluetooth network stream | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | Y
| Add latest value to an Observable collection of strings to output to the user on-screen | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | Y
5 | As a user, I want to be able to see the current temperatures from each different sensor on a graph | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
| Install OxyPlot | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Y
| Read the OxyPlot documentation and find tutorial | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Y
| Create new ObservableCollection of type DataPoint | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Y
| When a new latest reading has been retrieved add the temperature and time to the DataPoints Observable collection | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Y
| Bind the observable collection to the graph on the view | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Y
| Story Points Remaining | 122 | 28 | 14 | 14 | 12 | 34 | 0 | 20